## Decision Log
Decision ID | Date Raised | Date Required | Event | Category | Linked Record Type | Record ID | Request / Exception | Standard Rule | Exception Reason | Impact Summary | Severity | Driver | Approver | Contributors | Status | Decision | Rationale | Conditions | Action Owner | Action Due | Stakeholders to Notify | Effective Date | Expiry / Review Trigger | Precedent | Outcome / Verification | Supersedes | Superseded By | Last Updated
CONF-2026-042 | 2026-05-17 | 2026-05-18 | Annual Conference 2026 | Abstracts | Abstract | ABS-1438 | Allow submission after deadline following verified technical failure | Submissions closed 2026-05-15 | Author reported a documented technical failure before the deadline | Review assignments not yet finalized; limited fairness impact | Material | Abstract Manager | Programme Chair | Technical Support | Approved With Conditions | Late submission permitted | Issue occurred before deadline and did not disrupt reviewer assignment | Submission must be completed by 2026-05-18 12:00 UTC | Abstract Manager | 2026-05-18 | Author; Review Operations | 2026-05-17 | After submission deadline | One-time exception | Submission completed and routed to normal review |  |  | 2026-05-18
CONF-2026-087 | 2026-08-01 | 2026-08-03 | Annual Conference 2026 | Speakers | Speaker | SPK-221 | Replace accepted presenter with co-author | Presenter changes require programme approval | Original presenter cannot travel | Published programme and speaker records affected | Material | Programme Manager | Programme Chair | Speaker Manager | Approved With Conditions | Co-author approved as replacement | Replacement is an author on the accepted work and can meet presentation requirements | Replacement must register and complete speaker requirements by deadline | Speaker Manager | 2026-08-05 | Session Chair; Communications | 2026-08-01 | When replacement completes registration | Reusable precedent | Speaker and programme records updated |  |  | 2026-08-05
CONF-2026-104 | 2026-08-10 | 2026-08-11 | Annual Conference 2026 | Registration | Order | ORD-9308 | Refund requested after published deadline | Refund window has closed | Confidential exceptional circumstance reviewed separately | Financial and policy impact | Material | Registration Manager | Finance Lead | Event Director | Under Review |  | Pending authorized review | Do not store sensitive personal detail in shared log | Registration Manager | 2026-08-11 | Finance; Requester |  | Decision due | One-time exception | Pending |  |  | 2026-08-10

## README
Conference Decision Log & Approval Matrix
Purpose
Use this workbook to document material conference decisions and policy exceptions, assign approval authority, track conditions and follow-up actions, and preserve an audit trail.
Workflow
Request -> Rule -> Review -> Decision -> Action -> Record
How to use
1. Log only material decisions or exceptions that could affect fairness, money, programme delivery, contracts, or precedent.
2. Link each entry to the affected conference record (abstract, attendee, order, session, speaker, sponsor, vendor, etc.).
3. Use the Approval Matrix to identify the correct reviewer and approver before a decision is finalized.
4. Use standardized Status, Severity, Category, and Precedent fields to keep reporting consistent.
5. Record only the minimum necessary context. Do not place unnecessary sensitive personal information in the shared log.
6. Mark reversed decisions as Superseded rather than deleting history.
Color convention
Blue text | User-entered fields
Gray text | Static guidance / examples
Orange fill | Review or caution
Light red fill | Denied / high-risk / overdue attention

## Lists (hidden)
Category | Severity | Status | Precedent | Record Type
Registration | Routine | Proposed | One-time exception | Attendee
Abstracts | Material | Pending Information | Reusable precedent | Abstract
Peer Review | High Impact | Under Review | Policy clarification required | Review
Acceptance & Publication |  | Approved | Policy change recommended | Speaker
Speakers |  | Approved With Conditions |  | Session
Programme |  | Denied |  | Order
Sponsors & Exhibitors |  | Withdrawn |  | Sponsor
Accessibility & Participant Services |  | Implemented |  | Exhibitor
Onsite Operations |  | Expired |  | Vendor
Finance |  | Superseded |  | Venue
Venue |  |  |  | Other
Vendors
Governance

## Approval Matrix
Category | Exception / Decision Type | Initial Reviewer / Driver | Final Approver | Default Severity | Escalation Trigger | Backup Approver | Target Decision Time | Notes
Registration | Routine registration exception | Registration Manager | Event Manager | Routine | Policy override or material financial impact | Operations Lead | 1 business day | Use published registration/refund policy as baseline.
Registration | Refund after deadline / material fee waiver | Registration Manager | Finance Lead or authorized Event Director | Material | Large value, repeated precedent, or contractual issue | Event Director | 1 business day | Record minimum necessary context; keep sensitive details outside shared log.
Abstracts | Late abstract / submission deadline exception | Abstract Manager | Programme Chair | Material | Review assignments already issued or fairness concerns | Scientific Committee Chair | 1 business day | Document normal deadline and reason for exception.
Peer Review | Reviewer reassignment / invalid review / adjudication | Review Chair | Programme Chair | Material | Integrity concern or possible impact on final decision | Scientific Committee Chair | Same day to 2 business days | Link to review record; do not duplicate confidential review content.
Acceptance & Publication | Author change / publication eligibility exception | Programme Manager | Programme Chair | Material | Proceedings already finalized or publisher requirements affected | Proceedings Lead | 2 business days | Check publication and authorship rules.
Speakers | Speaker replacement / remote-presentation exception | Programme Manager | Programme Chair | Material | Programme already published or AV/contract implications | Event Director | 1 business day | Attach registration and speaker-compliance conditions where needed.
Programme | Room/time/session format change | Programme Manager | Event Director | Material | Capacity, accessibility, venue or sponsor impact | Programme Chair | Same day | Identify all stakeholders requiring notification.
Sponsors & Exhibitors | Benefit substitution / contract variation | Sponsorship Manager | Authorized Contract Owner / Event Director | Material | Financial value or contractual commitment changes | Finance Lead | 2 business days | Reference contract; do not log confidential commercial terms unnecessarily.
Accessibility & Participant Services | Operational accommodation exception | Participant Services Lead | Event Manager or designated Accessibility Lead | Material | Legal/compliance concern or major programme impact | Event Director | As soon as practicable | Store sensitive details only in restricted systems.
Onsite Operations | Access override / emergency operational change | Operations Lead | Event Director | High Impact | Safety, venue, capacity, or security concern | Designated Incident Lead | Immediate | Timestamp decisions and set review trigger.
Finance | Budget exception / unplanned spend | Budget Owner | Finance Lead | Material | Spend above delegated authority | Executive Sponsor | 1 business day | Follow organizational purchasing and delegation policy.
Governance | Policy precedent / ethics / high-risk exception | Relevant Functional Lead | Designated Committee or Executive Authority | High Impact | Research integrity, legal, reputational, or policy precedent risk | Executive Sponsor | Case-dependent | Use formal escalation; consider restricted/confidential handling.

## Open Actions
Open Actions View
Use this tab as a working view.
Filter the Decision Log for statuses such as Approved With Conditions or Under Review, then sort by Action Due.
Suggested review cadence
Planning phase: weekly
Final 30 days: daily
Event days: real time / shift handover
Post-event: until all actions are verified or archived